## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Fisheries Information System |  |  |  |  | COMPANY NAME | [6 empty] | B-AIM
PROJECT MANAGER |  | Sai Kishore Porupureddi |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project background and Broad Project Rational
1.1 | Project Profiling | Aashvik | 2021-01-11 | 2021-01-11 | 0 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Need for the Project / Project Scope | Aashvik | 2021-01-11 | 2021-01-11 | 0 | 100% | bar: WEEK 2 W
1.1.3 | Project Type | Ashvik | 2021-01-11 | 2021-01-11 | 0 | 100% | bar: WEEK 2 W to WEEK 3 W
1.2 | Project Proponent Details | Bhanu | 2021-01-11 | 2021-01-11 | 0 | 100% | bar: WEEK 2 R to WEEK 3 R
1.3 | Project Innovation / Potential . | Murali | 2021-01-11 | 2021-01-11 | 0 | 100% | bar: WEEK 3 M to WEEK 3 R
1.4 | Project Locations | Kishore | 2021-01-11 | 2021-01-11 | 0 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Corporate Social Responsibility | kishore | 2021-01-11 | 2021-01-11 | 0 | 100% | bar: WEEK 3 T to WEEK 3 R
2 | Project Technical Overview
2.1 | Project / sector specific analysis | Bhanu |  |  |  | 100% | bar: WEEK 4 M to WEEK 4 R
2.1.1 | Technology and manufacturing process | Bhanu |  |  |  | 100% | bar: WEEK 4 M to WEEK 4 R
2.1.2 | Locational analysis of the Project | Kishore |  |  |  | 100% | bar: WEEK 4 M to WEEK 4 R
2.1.3 | Commercial viability of Project/ Product | Kishore |  |  |  | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Project / sector specific growth projections | Aashvik |  |  |  | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Project manufacturing details | Murali |  |  |  | 100% | bar: WEEK 4 F to WEEK 5 F
2.3.1 | Assembly Line Workflow | Murali |  |  |  | 100% | bar: WEEK 4 F to WEEK 5 F
3 | Project Investment Overview
3.1 | Project cost and Means of Financing . | Shanmuk |  |  | 0 | 100%
3.2 | Project capex details | Shanmuk |  |  | 0 | 100%
3.3 | Project Structuring | Abhishek |  |  | 0 | 100%
3.4 | Project Technology Fee details | Abhishek |  |  | 0 | 100%
4 | Project Business Case
4.1 | Production Plan | Aashvik |  |  | 0 | 0%
4.2 | Marketing Plan | Bhanu |  |  | 0 | 0%
4.3 | Product Strategy | Murali
4.4 | Market Feasibility Analysis | Kishore
4.5 | Analysis with respect to strategic sector requirement | Shanmuk
4.5.1 | Sub-sector/market 1 analysis | Shanmuk
4.5.2 | Sub-sector/market 2 analysis | Bhanu
4.5.3 | Sub-sector/market 3 analysis | Murali
4.6 | Plan to develop and partner with upstream and downstream industries in India | Aashvik |  |  | 0 | 0%
4.7 | Project Benefits Assessment: | Kishore |  |  | 0 | 0%
5 | Project Implementation Strategy
5.1 | Project Phasing | Aashvik |  |  | 0 | 0%
5.2 | Organization Structure proposed | Bhanu |  |  | 0 | 0%
5.3 | Procurement/ Construction Details | Murali |  |  | 0 | 0%
5.4 | Other details | Kishore |  |  | 0 | 0%
6 | Project Execution Strategy .
6.1 | Project Institutional Framework | Shanmuk |  |  | 0 | 0%
6.2 | Infrastructure details and strategy for securing/ implementing the same | Aashvik |  |  | 0 | 0%
6.3 | Packaging, procurement and contracting strategy and framework | Bhanu |  |  | 0 | 0%
6.4 | Project management framework and philosophy | Murali
6.5 | Cost & Time overrun contingency measures and strategy | Kishore |  |  | 0 | 0%
7 | Project Risk Impact Analysis
7.1 | Project Risk/ Responsibility Matrix | Aashvik |  |  | 0 | 0%
7.2 | Project Financial Viability and Going Concern viability analysis and details | Bhanu |  |  | 0 | 0%
7.3 | Business Sustainability Plan | Murali
7.4 | Risk Analysis | Kishore
7.5 | Risk Mitigation Plan including costs associated with the individual plans | Shanmuk
7.6 | Detailed estimation of risk due to cost or time overruns and mitigation plans for the same | Aashvik
7.7 | Mitigation plan for Forex exposure risk | Bhanu
7.8 | Technology obsolescence risk assessment and mitigation plan | Murali
8 | Project Risk Impact Analysis
8.1 | Project Risk/ Responsibility Matrix | Kishore |  |  | 0 | 0%
8.1.1 | Project Financial Viability and Going Concern viability analysis and details | Kishore |  |  | 0 | 0%
8.1.2 | Business Sustainability Plan | Shanmuk
8.1.3 | Risk Analysis | Shanmuk
8.1.4 | Risk Mitigation Plan including costs associated with the individual plans | Bhanu
8.2 | Detailed estimation of risk due to cost or time overruns and mitigation plans for the same | Aashvik
8.2.1 | Environmental Components | Aashvik
8.2.2 | Impacts, Mitigation, and Monitoring Summary | Bhanu
8.2.3 | Risk Assessments | Bhanu
8.2.4 | Environmental Management Framework | Murali
8.3 | Project Alternatives | Kishore
8.4 | Statement of Commitments | Shanmuk